## Slide 1
TIRE-DERIVED FUEL · MASTER PROCESS MAP
South America → Pakistan
Cement Plant Supply Chain Flow Chart
End-to-end process map covering client sourcing, regulatory approvals, ocean transit, customs clearance, inland delivery and kiln co-processing — with all required documents at each step.
9
Phases
60–90
Day cycle
HS 4012.20
Tariff code
B3140
Basel annex
Confidential · Internal & Client-Facing

## Slide 2
End-to-End Process — Master View
Nine sequential phases from supplier identification to Basel closure
TDF Supply Chain · South America → Pakistan Cement Plant
1
Client Sourcing
& Qualification
2
Pre-Shipment
Preparation
3
Regulatory
Approvals
4
Origin Customs
& Vessel Loading
5
Ocean Transit
35–55 days
6
Pakistan Customs
Clearance
7
Inland Transport
to Plant
8
Plant Receipt &
Kiln Co-Processing
9
Closure, Basel
& Settlement
Origin operations
Regulatory / compliance
Logistics / transit
Destination operations
Closure & reporting
Critical sequencing rule
Phase 3 (Basel notification + Pak-EPA NOC + cement-plant co-processing license) must be FULLY APPROVED before Phase 4 loading. Pre-loading without acknowledgments from both Competent Authorities risks port seizure and forced re-export.

## Slide 3
Phase 1 — Client Sourcing & Qualification
Identify, audit and contract scrap-tire generators in any South American origin
ORIGIN
TDF Supply Chain · South America → Pakistan Cement Plant
PROCESS STEPS
1
Lead generation — fleet operators, retread shops, mining sites, scrap yards, municipalities.
2
Initial outreach & NDA — confidentiality agreement signed before exchanging volumes & pricing.
3
Inventory audit — site visit, photos, tonnage estimate, casing condition, contamination check.
4
Sample acceptance vs. cement-kiln spec — CV 28–32 MJ/kg, moisture <2%, Cl <0.5%, S <2%.
5
Commercial offer — USD/MT, Incoterms (FOB/CIF/DAP), payment (LC at sight or 30-day TT), volume.
6
Supply agreement signed — quality spec annexed; failure-mode clauses included.
DOCUMENTS PRODUCED
▤
Mutual NDA
▤
Letter of Intent (LOI)
▤
Site inspection report (photos + tonnage)
▤
Quality specification sheet (kiln-grade)
⚠
Supply & Purchase Agreement (SPA)
▤
KYC / AML pack on supplier

## Slide 4
Phase 2 — Pre-Shipment Preparation
Sorting, optional shredding, decontamination, consolidation, independent inspection & loading
ORIGIN
TDF Supply Chain · South America → Pakistan Cement Plant
PROCESS STEPS
1
Sorting & grading — separate whole tires from scrap, remove rims and metal rings as required.
2
Optional shredding — to 50–150 mm chips for main-burner injection; whole tires for precalciner.
3
Decontamination — remove soil, water, organic debris (vector-control mandatory in BR/CO).
4
Consolidation to container quantity — ≈ 22 MT whole / 25 MT shred per 40' HC.
5
Pre-Shipment Inspection (PSI) — SGS · Bureau Veritas · Intertek · Cotecna; quantity, quality, photos.
6
Supervised stuffing & sealing — bolt + cable seal numbers logged; photo archive.
DOCUMENTS PRODUCED
▤
Weighbridge tickets (per truck in)
▤
Container packing list
⚠
Pre-Shipment Inspection (PSI) certificate
▤
Fumigation / phytosanitary certificate
▤
Vector-control declaration
▤
Loading photo log + seal register
▤
Certificate of Analysis (CoA)

## Slide 5
Phase 3 — Regulatory & Cross-Border Approvals
Basel notifications + origin export permits + Pakistan import NOCs — must be in place BEFORE loading
COMPLIANCE
TDF Supply Chain · South America → Pakistan Cement Plant
PROCESS STEPS
1
Basel Convention prior notification — HS 4012.20; Annex IX B3140 preferred. Both CAs must acknowledge in writing.
2
Origin environmental export authorization — BR-IBAMA · CL-MMA · AR-SAyDS · PE-MINAM · CO-ANLA · UY-MA.
3
Pak-EPA NOC — issued under Hazardous Substances Rules 2003.
4
Provincial EPA NOC — Sindh / Punjab / KP per cement-plant location.
5
MoCC approval — Pakistan's Basel Competent Authority sign-off.
6
Cement plant co-processing license — facility authorized under SRO; capacity letter attached.
7
SBP / EIF registration — via importer's bank; LC opened or TT advance arranged.
DOCUMENTS PRODUCED
⚠
Basel Notification Document — Annex IA
⚠
Basel Movement Document — Annex IB
▤
Origin export environmental permit
⚠
Pak-EPA NOC (federal)
▤
Provincial EPA NOC
▤
MoCC / Basel CA approval letter
▤
Co-processing authorization & capacity letter
▤
Bank EIF / LC / TT advice

## Slide 6
Phase 4 — Origin Customs & Vessel Loading
Export declaration, terminal handover, vessel booking, Bill of Lading, marine insurance
ORIGIN
TDF Supply Chain · South America → Pakistan Cement Plant
PROCESS STEPS
1
Customs export declaration — BR DU-E · CL DUS · AR DJVE · PE DAM · CO DEX · UY DUA.
2
Anti-narcotic / canine inspection — mandatory in CO / PE / EC; risk-based elsewhere.
3
Container handed to terminal — against Equipment Interchange Receipt.
4
Vessel booking confirmed — Hapag-Lloyd · MSC · Maersk · CMA CGM · ONE · ZIM.
5
Mate's receipt issued — on board → original Bill of Lading printed by line.
6
Marine cargo insurance — Institute Cargo Clauses A or C; value = CIF × 110%.
DOCUMENTS PRODUCED
▤
Customs export declaration
⚠
Commercial Invoice
⚠
Packing List
⚠
Bill of Lading (original 3/3)
▤
Certificate of Origin
▤
Marine insurance certificate
▤
Mate's receipt + EIR
▤
Anti-narcotic clearance

## Slide 7
Phase 5 — Ocean Transit
35–55 days at sea with shipping-line tracking, ETA updates and active cargo cover
TRANSIT
TDF Supply Chain · South America → Pakistan Cement Plant
PROCESS STEPS
1
East-coast routing — Santos · Buenos Aires · Montevideo → Cape of Good Hope → Karachi (40–50 days).
2
West-coast routing — San Antonio · Callao · Buenaventura → Panama → Suez → Karachi (45–55 days).
3
Daily / weekly tracking — via line booking; ETAs pushed to importer + plant logistics.
4
Document courier — originals (B/L, COO, CoA, Annex IB) sent via DHL / FedEx so docs arrive ahead of vessel.
5
Insurance active — warehouse-to-warehouse from origin yard to plant gate.
DOCUMENTS PRODUCED
▤
Vessel tracking log
▤
Courier airway bill
▤
Updated ETA notices
▤
Deviation / general-average notices

## Slide 8
Phase 6 — Pakistan Port Arrival & Customs Clearance
Karachi Port / Port Qasim — WeBOC declaration, EPA examination, duty payment, release
PAKISTAN
TDF Supply Chain · South America → Pakistan Cement Plant
PROCESS STEPS
1
Arrival notice — issued by line; importer pays charges & surrenders OBL → Delivery Order.
2
Goods Declaration filed in WeBOC — PCT 4012.20.00; clearing agent assigned.
3
Customs assessment — physical examination, weighing, document scrutiny.
4
Pak-EPA / MoCC examination — verifies federal NOC, Annex IB, co-processing endorsement.
5
Duty & tax — Customs duty + GST + WHT + ACD; check applicable SRO concessions.
6
Release order — container picked up by inland trucker.
DOCUMENTS PRODUCED
▤
Arrival notice + Delivery Order
⚠
Goods Declaration (WeBOC)
▤
Duty & tax payment challans
▤
Customs examination report
⚠
EPA / MoCC examination report
▤
Annex IB countersigned at port
▤
Out-of-Charge / Release order

## Slide 9
Phase 7 — Inland Transport to Cement Plant
Trucking from Karachi / Port Qasim to plant gate (100 km – 1,500 km)
TRANSIT
TDF Supply Chain · South America → Pakistan Cement Plant
PROCESS STEPS
1
Trucker dispatched — flatbed or tipper based on TDF format; route plan agreed.
2
Plant routing — Lucky Karachi 100 km · DG Khan ~1,200 · Maple Leaf ~1,300 · Bestway Hattar ~1,400.
3
Weighbridge readings — at port-out and plant-in; both retained for reconciliation.
4
Plant gate receipt — container handed for de-vanning.
DOCUMENTS PRODUCED
▤
Inland transport waybill / bilty
▤
Trucker insurance certificate
▤
Port-out + plant-in weighbridge tickets
▤
Plant gate receipt (signed)

## Slide 10
Phase 8 — Plant Receipt & Kiln Co-Processing
Quality verification, acceptance, kiln feed, emission monitoring, final destruction certificate
PAKISTAN
TDF Supply Chain · South America → Pakistan Cement Plant
PROCESS STEPS
1
Lab quality verification — moisture, CV, ash, Cl, S, metals (Hg, Cd, Pb).
2
Acceptance certificate — issued (or rejection / partial acceptance lodged).
3
Storage — covered yard or dedicated TDF silo to prevent moisture pickup.
4
Kiln feed — whole tires at precalciner; shred at main burner. Substitution rate 10–25%.
5
Continuous emission monitoring — dioxins/furans, HCl, SOx, NOx vs. Pakistan NEQS.
6
Final destruction certificate — issued by plant — closes the Basel loop.
DOCUMENTS PRODUCED
▤
Plant lab analysis report
▤
Acceptance / rejection certificate
▤
Co-processing log (date, tonnage, kiln)
▤
Emission monitoring records (CEMS)
⚠
Final destruction / disposal certificate

## Slide 11
Phase 9 — Closure, Basel Return & Settlement
Annex IB returned within 180 days · supplier paid · annual reporting · re-order
CLOSURE
TDF Supply Chain · South America → Pakistan Cement Plant
PROCESS STEPS
1
Basel Annex IB — signed by importer/disposer → returned to exporter → submitted to origin CA within 180 days.
2
Payment release — to South American supplier per LC terms or TT.
3
Annual Basel report — filed by exporter to origin CA — total volumes, breakdown, incidents.
4
Performance review — with cement plant — quality, substitution, emissions, savings vs. coal.
5
Re-order — next purchase order under standing supply agreement.
DOCUMENTS PRODUCED
⚠
Signed Annex IB returned to origin CA
▤
SWIFT / payment proof to supplier
▤
Annual Basel report
▤
Plant performance scorecard
▤
Next PO + shipping instruction

## Slide 12
Compliance Quick Reference
Key authorities, codes and ports across both ends of the chain
TDF Supply Chain · South America → Pakistan Cement Plant
Origin (South America)
• Basel Convention — used pneumatic tires (B3140)
• BR IBAMA · CL MMA · AR SAyDS · PE MINAM · CO ANLA · UY MA
• HS code 4012.20
• Origin ports: Santos, Buenos Aires, San Antonio,
• Callao, Buenaventura, Paranaguá
Pakistan
• Pak-EPA NOC (Hazardous Substances Rules 2003)
• Provincial EPA NOC (Sindh / Punjab / KP)
• MoCC — Basel Competent Authority
• Cement plant co-processing license under SRO
• WeBOC GD · PCT 4012.20.00
• Ports: Karachi (KPT) · Port Qasim (PQA)
Critical Documents (must travel with shipment)
• Bill of Lading (original) · Commercial Invoice · Packing List
• Certificate of Origin
• Basel Annex IB (Movement Document)
• PSI certificate · Marine insurance
• Pak-EPA NOC · Provincial NOC · MoCC approval
• Cement plant co-processing authorization
Top Failure Modes to Avoid
• Loading before Basel notification acknowledged by both CAs
• HS-code misclassification (4012.20 vs 4004) → Customs hold
• Moisture > 2% on arrival → kiln rejection
• Rims attached when plant requires whole-tire-no-metal
• Annex IB not returned in 180 days → next-shipment block
• Provincial EPA NOC missed → port-side seizure

## Slide 13
Master Document Checklist by Phase
Single page — every document required across the 9 phases
TDF Supply Chain · South America → Pakistan Cement Plant
PHASE 1 — Sourcing
▤ NDA · LOI · Site inspection report
▤ Quality spec · SPA · KYC pack
PHASE 2 — Pre-shipment
▤ Weighbridge · Packing list · PSI certificate
▤ Fumigation · Vector-control · Photos · CoA
PHASE 3 — Regulatory
▤ Basel Annex IA + IB
▤ Origin export permit · Pak-EPA NOC
▤ Provincial EPA NOC · MoCC approval
▤ Co-processing license · EIF / LC
PHASE 4 — Customs / Loading
▤ Export declaration · Commercial invoice
▤ Packing list · BL · COO
▤ Marine insurance · EIR · Anti-narcotic
PHASE 5 — Transit
▤ Tracking log · Courier AWB
▤ ETA notices · Deviation notices
PHASE 6 — Pakistan Customs
▤ Arrival notice + DO
▤ WeBOC Goods Declaration · Duty challans
▤ Customs examination report
▤ EPA / MoCC examination · Annex IB countersigned
▤ Out-of-Charge / Release order
PHASE 7 — Inland
▤ Transport waybill · Trucker insurance
▤ Port-out + plant-in weighbridge tickets
▤ Plant gate receipt
PHASE 8 — Plant / Kiln
▤ Lab analysis report
▤ Acceptance certificate
▤ Co-processing log · CEMS records
▤ Final destruction certificate
PHASE 9 — Closure
▤ Signed Annex IB returned (180 days)
▤ Payment proof · Annual Basel report
▤ Performance scorecard · Next PO